## Project Charter
Project Charter for Group {05}
Project Title: {WePlan_travels}
Project Manager | Zakaria Davids
Project start date: | 2025-08-04 | Project end date: | 2025-08-22
E-Commerce Business Idea Concept
WePlan_travels is an e-commerce travel platform designed to let customers book flights, accommodation, transport, and activities in one place. The project is being undertaken because most travelers currently use several websites, which is time-consuming and confusing. By creating a single, secure, and easy-to-use system, WePlan_travels aims to make travel planning faster, cheaper, and more reliable. The business case is clear: there is a growing demand for digital solutions that bring convenience and trust to travel bookings. This project will not only improve customer experience but also position WePlan_travels as a competitive brand in the online travel market.
Project objectives: This section addresses how the project ties into the group's strategic e-commerce goals, and includes the project objectives that support those goals. |  |  |  | Benefits: Benefits to potential stakeholders by doing the project .
1.Develop a fully functional e-commerce travel platform that integrates flights, accommodation, transport, and activities into a single booking system. |  |  |  | 1.Customers gain convenience by booking all travel needs (flights, hotels, cars, activities) on one trusted platform.
2.Implement secure online payment solutions to build customer trust and ensure safe transactions. |  |  |  | 2.The project team develops practical e-commerce and teamwork skills that can be applied in real-world careers.
3.Enhance customer experience by creating a simple, user-friendly interface that reduces booking time and effort. |  |  |  | 3.WePlan_travels as a business idea benefits by testing how an online travel platform could work, giving early insight into possible challenges and opportunities in the e-commerce travel market.
4.Strengthen WePlan_travels’ market presence by using digital marketing strategies (e.g., Instagram) to attract and retain customers. |  |  |  | 4.Stakeholders and partners benefit by seeing the potential of a travel platform that could grow into a competitive business with further development.
Stakeholder Requirements: |  |  |  | Project stakeholders:
The stakeholders of WePlan_travels have several high-level requirements that guide the project. Customers need a secure, reliable, and easy-to-use platform where they can book flights, accommodation, transport, and activities in one place. The project team requires clear roles, good collaboration, and access to the necessary tools and resources to build and manage the system effectively. As a business idea, WePlan_travels requires a functional prototype that demonstrates its potential in the online travel market. Potential partners, such as airlines, hotels, and car rental services, need a platform that can eventually integrate their offerings and reach more customers. |  |  |  | The project stakeholders for WePlan_travels include both internal and external parties. Internally, the project team and project manager are directly involved in developing and managing the platform. Externally, customers who use the platform, travel partners such as airlines, hotels, and car rental services, and potential investors or advisors are influenced by the project. All these stakeholders are either directly using, supporting, or benefiting from the platform in some way.
Deliverables: List the core requirements of your e-commerce website. This includes functional and non-functional requirements.
Functional |  | 3.Allow users to create, update, and manage personal accounts and profiles. |  | Non-functional requirements | 3.Maintain fast performance even when multiple users access the system simultaneously.
1.Allow users to view and select available flights, hotels, car rentals, and activities based on their chosen dates, destination, and preferences. |  | 4.Send booking confirmations and notifications via email. |  | 1.Ensure the platform is secure and protects user data. | 4.Ensure high reliability and uptime so users can access the platform anytime.
2.Enable secure online payment for all bookings. |  | 5.Provide an admin interface to manage listings, bookings, and user information. |  | 2.Provide a responsive interface that works well on desktop and mobile devices. | 5.Follow clear coding standards and maintainable architecture for future updates
Roles and responsibilities:
Name | Surname | Student number | Role | Cellphone | Email
Zakaria | Davids | N/A | Project Manager(Frontend Developer) | 078 631 0966 | zakariadavids7@gmail.com
Oyama | Masekwana | N/A | Data administrator & Website administrator | 072 039 3095 | masekwanaoyama7@gmail.com
Brayn | Meyer | N/A | Backend Developer | 064 972 1546 | coolmrepic9876@gmail.com
Yolisa | Nomngcayi | N/A | Data administrator | 074 466 5255 | yolisanomgcayi@gmail.com
Zayaan | Salie | N/A | Website administator | 061 104 6715 | zayaansalie91@gmail.com
Scope: |  |  |  | Out of Scope:
The scope of the WePlan_travels project includes the full development and testing of an online travel booking platform that allows customers to book flights, hotels, car rentals, and activities in one place. It covers implementing secure payment processing, user account management, and email notifications for bookings. The project will deliver an intuitive and responsive website accessible on both desktop and mobile devices. Additionally, it involves creating an admin interface to manage listings, bookings, and user information efficiently. Marketing efforts, such as social media promotion and digital campaigns, are also included to attract and engage users, establishing WePlan_travels as a competitive travel booking platform. |  |  |  | The following features are considered “nice to have” and are out of scope for the current WePlan_travels project due to time and resource constraints. These include integrating real-time flight and hotel availability APIs, implementing multi-language and multi-currency support, adding customer reviews and ratings for bookings, providing a mobile app version of the platform, and offering AI-based personalized travel recommendations. While these features could enhance the user experience, they are not part of the core deliverables for this project.
Risks: |  |  | Constraints: |  | Mitigation:
The WePlan_travels project faces several potential risks. These include security risks such as data breaches or payment fraud, which could affect customer trust. Technical risks may arise from system bugs, slow performance, or server downtime that could disrupt bookings. There is also a risk of delayed development due to resource constraints or team availability. Market risks include low user adoption or competition from established travel booking platforms. Finally, integration risks could occur if third-party services (flights, hotels, car rentals) are not properly connected or updated. |  |  | The WePlan_travels project is limited by several constraints. These include time, as the project must be completed within the scheduled period. Budget limitations may restrict access to premium tools, third-party APIs, or advanced features. Technical constraints, such as team expertise and available server resources, may affect system performance or functionality. Additionally, scope limitations mean that only core features will be implemented, while advanced or “nice-to-have” features may not be included in this phase of the project. |  | To reduce potential risks, the WePlan_travels team will implement secure coding practices and use reliable payment gateways to protect customer data. Regular testing and quality assurance will help identify and fix system bugs or performance issues. Clear project planning, task allocation, and time management will minimize delays. Market risks will be addressed through digital marketing and user engagement strategies to attract customers. For integration challenges, the team will use tested APIs and maintain close communication with third-party service providers to ensure smooth connectivity.
Assumptions: Known factors about the project that are not flexible.
The WePlan_travels project assumes that users have internet access and basic digital literacy to use the platform. It is assumed that third-party travel service providers (airlines, hotels, car rentals) will supply accurate and up-to-date information for bookings. The project assumes the team has access to the necessary development tools and resources. It is also assumed that the timeline and budget set for the project will remain consistent, and that stakeholders will provide timely feedback when required.
Comments/Notes:
This project is a prototype for an online travel booking platform that makes it easier for customers to plan trips. The team will focus on core features like booking flights, hotels, cars, and activities, while advanced features such as a mobile app or AI recommendations may be added later. The platform will be secure, reliable, and easy to use. Feedback from users and stakeholders will help improve the system in the future. The project also gives the team practical experience in building an e-commerce website and working together effectively.